## 시트1
Task Name | Duration | Start | End | Date
|  |  |  | Oct 7 | Oct 8 | Oct 9 | Oct 10 | Oct 11 | Oct 12 | Oct 13 | Oct 14
1. Preparation
1.1. Task distribution for each members | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
1.2. Github set-up as the software repository | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
1.3. Taiga set-up as project management software | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
1.4. Google Drive set-up as the files repository | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
1.5. Group creation in Discord and Telegram for communication | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2. Software Development (per user story)
2.1. Login as a system admin
2.1.1. Planning
2.1.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.1.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.1.2. Designs
2.1.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.1.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.1.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.1.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.1.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.1.3. Programming
2.1.3.1. Front-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.1.3.2. Back-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.1.3. Testing | 4 days | Oct 11, 2022 | Oct 14, 2022 | bar: Date Oct 11 to Date Oct 14
2.2. Logout from the system (System Admin)
2.2.1. Planning
2.2.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.2.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.2.2. Designs
2.2.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.2.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.2.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.2.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.2.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.2.3. Programming
2.2.3.1. Front-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.2.3.2. Back-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.2.3. Testing | 4 days | Oct 11, 2022 | Oct 14, 2022 | bar: Date Oct 11 to Date Oct 14
2.3. Login as an author
2.3.1. Planning
2.3.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.3.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.3.2. Designs
2.3.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.3.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.3.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.3.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.3.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.3.3. Programming
2.3.3.1. Front-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.3.3.2. Back-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.3.3. Testing | 4 days | Oct 11, 2022 | Oct 14, 2022 | bar: Date Oct 11 to Date Oct 14
2.4. Logout from the system (Author)
2.4.1. Planning
2.4.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.4.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.4.2. Designs
2.4.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.4.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.4.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.4.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.4.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.4.3. Programming
2.4.3.1. Front-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.4.3.2. Back-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.4.3. Testing | 4 days | Oct 11, 2022 | Oct 14, 2022 | bar: Date Oct 11 to Date Oct 14
2.5. Login as a conference chair
2.5.1. Planning
2.5.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.5.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.5.2. Designs
2.5.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.5.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.5.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.5.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.5.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.5.3. Programming
2.5.3.1. Front-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.5.3.2. Back-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.5.3. Testing | 4 days | Oct 11, 2022 | Oct 14, 2022 | bar: Date Oct 11 to Date Oct 14
2.6. Logout from the system (Conference Chair)
2.6.1. Planning
2.6.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.6.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.6.2. Designs
2.6.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.6.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.6.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.6.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.6.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.6.3. Programming
2.6.3.1. Front-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.6.3.2. Back-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.6.3. Testing | 4 days | Oct 11, 2022 | Oct 14, 2022 | bar: Date Oct 11 to Date Oct 14
2.7. Login as a reviewer
2.7.1. Planning
2.7.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.7.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.7.2. Designs
2.7.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.7.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.7.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.7.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.7.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.7.3. Programming
2.7.3.1. Front-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.7.3.2. Back-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.7.3. Testing | 4 days | Oct 11, 2022 | Oct 14, 2022 | bar: Date Oct 11 to Date Oct 14
2.8. Logout from the system (Reviewer)
2.8.1. Planning
2.8.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.8.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.8.2. Designs
2.8.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.8.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.8.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.8.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.8.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.8.3. Programming
2.8.3.1. Front-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.8.3.2. Back-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.8.3. Testing | 4 days | Oct 11, 2022 | Oct 14, 2022 | bar: Date Oct 11 to Date Oct 14
2.9. Create user (System Admin)
2.9.1. Planning
2.9.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.9.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.9.2. Designs
2.9.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.9.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.9.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.9.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.9.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.9.3. Programming
2.9.3.1. Front-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.9.3.2. Back-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.9.3. Testing | 4 days | Oct 11, 2022 | Oct 14, 2022 | bar: Date Oct 11 to Date Oct 14
2.10. View users (System Admin)
2.10.1. Planning
2.10.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.10.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.10.2. Designs
2.10.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.10.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.10.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.10.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.10.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.10.3. Programming
2.10.3.1. Front-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.10.3.2. Back-end Programming | 2 days | Oct 10, 2022 | Oct 11, 2022 | bar: Date Oct 10 to Date Oct 11
2.10.3. Testing | 4 days | Oct 11, 2022 | Oct 14, 2022 | bar: Date Oct 11 to Date Oct 14
2.11. Update author (System Admin)
2.11.1. Planning
2.11.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.11.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.11.2. Designs
2.11.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.11.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.11.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.11.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.11.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.11.3. Programming
2.11.3.1. Front-end Programming | 2 days | Oct 12, 2022 | Oct 13, 2022 | bar: Date Oct 12 to Date Oct 13
2.11.3.2. Back-end Programming | 2 days | Oct 12, 2022 | Oct 13, 2022 | bar: Date Oct 12 to Date Oct 13
2.11.3. Testing | 2 days | Oct 13, 2022 | Oct 14, 2022 | bar: Date Oct 13 to Date Oct 14
2.12. Update reviewer (System Admin)
2.12.1. Planning
2.12.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.12.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.12.2. Designs
2.12.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.12.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.12.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.12.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.12.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.12.3. Programming
2.12.3.1. Front-end Programming | 2 days | Oct 12, 2022 | Oct 13, 2022 | bar: Date Oct 12 to Date Oct 13
2.12.3.2. Back-end Programming | 2 days | Oct 12, 2022 | Oct 13, 2022 | bar: Date Oct 12 to Date Oct 13
2.12.3. Testing | 2 days | Oct 13, 2022 | Oct 14, 2022 | bar: Date Oct 13 to Date Oct 14
2.13. Update conference chair (System Admin)
2.13.1. Planning
2.13.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.13.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.13.2. Designs
2.13.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.13.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.13.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.13.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.13.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.13.3. Programming
2.13.3.1. Front-end Programming | 2 days | Oct 12, 2022 | Oct 13, 2022 | bar: Date Oct 12 to Date Oct 13
2.13.3.2. Back-end Programming | 2 days | Oct 12, 2022 | Oct 13, 2022 | bar: Date Oct 12 to Date Oct 13
2.13.3. Testing | 2 days | Oct 13, 2022 | Oct 14, 2022 | bar: Date Oct 13 to Date Oct 14
2.14. Update system admin (System Admin)
2.14.1. Planning
2.14.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.14.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.14.2. Designs
2.14.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.14.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.14.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.14.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.14.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.14.3. Programming
2.14.3.1. Front-end Programming | 2 days | Oct 12, 2022 | Oct 13, 2022 | bar: Date Oct 12 to Date Oct 13
2.14.3.2. Back-end Programming | 2 days | Oct 12, 2022 | Oct 13, 2022 | bar: Date Oct 12 to Date Oct 13
2.14.3. Testing | 2 days | Oct 13, 2022 | Oct 14, 2022 | bar: Date Oct 13 to Date Oct 14
2.15. Update role of author (System Admin)
2.15.1. Planning
2.15.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.15.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.15.2. Designs
2.15.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.15.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.15.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.15.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.15.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.15.3. Programming
2.15.3.1. Front-end Programming | 2 days | Oct 12, 2022 | Oct 13, 2022 | bar: Date Oct 12 to Date Oct 13
2.15.3.2. Back-end Programming | 2 days | Oct 12, 2022 | Oct 13, 2022 | bar: Date Oct 12 to Date Oct 13
2.15.3. Testing | 2 days | Oct 13, 2022 | Oct 14, 2022 | bar: Date Oct 13 to Date Oct 14
2.16. Update role of reviewer (System Admin)
2.16.1. Planning
2.16.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.16.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.16.2. Designs
2.16.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.16.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.16.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.16.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.16.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.16.3. Programming
2.16.3.1. Front-end Programming | 2 days | Oct 12, 2022 | Oct 13, 2022 | bar: Date Oct 12 to Date Oct 13
2.16.3.2. Back-end Programming | 2 days | Oct 12, 2022 | Oct 13, 2022 | bar: Date Oct 12 to Date Oct 13
2.16.3. Testing | 2 days | Oct 13, 2022 | Oct 14, 2022 | bar: Date Oct 13 to Date Oct 14
2.17. Update role of conference chair (System Admin)
2.17.1. Planning
2.17.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.17.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.17.2. Designs
2.17.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.17.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.17.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.17.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.17.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.17.3. Programming
2.17.3.1. Front-end Programming | 2 days | Oct 12, 2022 | Oct 13, 2022 | bar: Date Oct 12 to Date Oct 13
2.17.3.2. Back-end Programming | 2 days | Oct 12, 2022 | Oct 13, 2022 | bar: Date Oct 12 to Date Oct 13
2.17.3. Testing | 2 days | Oct 13, 2022 | Oct 14, 2022 | bar: Date Oct 13 to Date Oct 14
2.18. Update role of system admin (System Admin)
2.18.1. Planning
2.18.1.1. User Story | Less than a day | Oct 7, 2022 | Oct 7, 2022 | bar: Date Oct 7
2.18.1.2. Use Case Description | 2 days | Oct 7, 2022 | Oct 8, 2022 | bar: Date Oct 7 to Date Oct 8
2.18.2. Designs
2.18.2.1. BCE + UML Diagram | 2 days | Oct 8, 2022 | Oct 9, 2022 | bar: Date Oct 8 to Date Oct 9
2.18.2.2. Sequence Diagram | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.18.2.3. Wireframe | Less than a day | Oct 10, 2022 | Oct 10, 2022 | bar: Date Oct 10
2.18.2.4. Data Persistent | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.18.2.5. Test Case | 2 days | Oct 9, 2022 | Oct 10, 2022 | bar: Date Oct 9 to Date Oct 10
2.18.3. Programming
2.18.3.1. Front-end Programming | 2 days | Oct 12, 2022 | Oct 13, 2022 | bar: Date Oct 12 to Date Oct 13
2.18.3.2. Back-end Programming | 2 days | Oct 12, 2022 | Oct 13, 2022 | bar: Date Oct 12 to Date Oct 13
2.18.3. Testing | 2 days | Oct 13, 2022 | Oct 14, 2022 | bar: Date Oct 13 to Date Oct 14
2.19. Class Diagram | 3 days | Oct 12, 2022 | Oct 14, 2022 | bar: Date Oct 12 to Date Oct 14