## 시트1
Task Name | Duration | Start | End | Date
|  |  |  | Oct 14 | Oct 15 | Oct 16 | Oct 17 | Oct 18 | Oct 19 | Oct 20 | Oct 21
1. External Tasks
1.1. Task distribution for each members | Less than a day | Oct 14, 2022 | Oct 14, 2022 | bar: Date Oct 14
1.2. Create a list of prioritized use cases | Less than a day | Oct 14, 2022 | Oct 14, 2022 | bar: Date Oct 14
1.3. Taiga follow-up as project management software | Less than a day | Oct 14, 2022 | Oct 14, 2022 | bar: Date Oct 14
1.4. Google Drive follow-up as the files repository | Less than a day | Oct 14, 2022 | Oct 14, 2022 | bar: Date Oct 14
2. Software Development (per user story)
2.1. Submit papers (Author)
2.1.1. Planning
2.1.1.1. User Story | Less than a day | Oct 14, 2022 | Oct 14, 2022 | bar: Date Oct 14
2.1.1.2. Use Case Description | 2 days | Oct 14, 2022 | Oct 15, 2022 | bar: Date Oct 14 to Date Oct 15
2.1.2. Designs
2.1.2.1. BCE + UML Diagram | 2 days | Oct 15, 2022 | Oct 16, 2022 | bar: Date Oct 15 to Date Oct 16
2.1.2.2. Sequence Diagram | 2 days | Oct 16, 2022 | Oct 17, 2022 | bar: Date Oct 16 to Date Oct 17
2.1.2.3. Wireframe | Less than a day | Oct 17, 2022 | Oct 17, 2022 | bar: Date Oct 17
2.1.2.4. Data Persistent | 2 days | Oct 16, 2022 | Oct 17, 2022 | bar: Date Oct 16 to Date Oct 17
2.1.2.5. Test Case | 2 days | Oct 16, 2022 | Oct 17, 2022 | bar: Date Oct 16 to Date Oct 17
2.1.3. Programming
2.1.3.1. Front-end Programming | 2 days | Oct 17, 2022 | Oct 18, 2022 | bar: Date Oct 17 to Date Oct 18
2.1.3.2. Back-end Programming | 2 days | Oct 17, 2022 | Oct 18, 2022 | bar: Date Oct 17 to Date Oct 18
2.1.3. Testing | 4 days | Oct 18, 2022 | Oct 21, 2022 | bar: Date Oct 18 to Date Oct 21
2.2. View submitted paper (Author)
2.2.1. Planning
2.2.1.1. User Story | Less than a day | Oct 14, 2022 | Oct 14, 2022 | bar: Date Oct 14
2.2.1.2. Use Case Description | 2 days | Oct 14, 2022 | Oct 15, 2022 | bar: Date Oct 14 to Date Oct 15
2.2.2. Designs
2.2.2.1. BCE + UML Diagram | 2 days | Oct 15, 2022 | Oct 16, 2022 | bar: Date Oct 15 to Date Oct 16
2.2.2.2. Sequence Diagram | 2 days | Oct 16, 2022 | Oct 17, 2022 | bar: Date Oct 16 to Date Oct 17
2.2.2.3. Wireframe | Less than a day | Oct 17, 2022 | Oct 17, 2022 | bar: Date Oct 17
2.2.2.4. Data Persistent | 2 days | Oct 16, 2022 | Oct 17, 2022 | bar: Date Oct 16 to Date Oct 17
2.2.2.5. Test Case | 2 days | Oct 16, 2022 | Oct 17, 2022 | bar: Date Oct 16 to Date Oct 17
2.2.3. Programming
2.2.3.1. Front-end Programming | 2 days | Oct 17, 2022 | Oct 18, 2022 | bar: Date Oct 17 to Date Oct 18
2.2.3.2. Back-end Programming | 2 days | Oct 17, 2022 | Oct 18, 2022 | bar: Date Oct 17 to Date Oct 18
2.2.3. Testing | 4 days | Oct 18, 2022 | Oct 21, 2022 | bar: Date Oct 18 to Date Oct 21
2.3. Update submitted paper (Author)
2.3.1. Planning
2.3.1.1. User Story | Less than a day | Oct 14, 2022 | Oct 14, 2022 | bar: Date Oct 14
2.3.1.2. Use Case Description | 2 days | Oct 14, 2022 | Oct 15, 2022 | bar: Date Oct 14 to Date Oct 15
2.3.2. Designs
2.3.2.1. BCE + UML Diagram | 2 days | Oct 15, 2022 | Oct 16, 2022 | bar: Date Oct 15 to Date Oct 16
2.3.2.2. Sequence Diagram | 2 days | Oct 16, 2022 | Oct 17, 2022 | bar: Date Oct 16 to Date Oct 17
2.3.2.3. Wireframe | Less than a day | Oct 17, 2022 | Oct 17, 2022 | bar: Date Oct 17
2.3.2.4. Data Persistent | 2 days | Oct 16, 2022 | Oct 17, 2022 | bar: Date Oct 16 to Date Oct 17
2.3.2.5. Test Case | 2 days | Oct 16, 2022 | Oct 17, 2022 | bar: Date Oct 16 to Date Oct 17
2.3.3. Programming
2.3.3.1. Front-end Programming | 2 days | Oct 17, 2022 | Oct 18, 2022 | bar: Date Oct 17 to Date Oct 18
2.3.3.2. Back-end Programming | 2 days | Oct 17, 2022 | Oct 18, 2022 | bar: Date Oct 17 to Date Oct 18
2.3.3. Testing | 4 days | Oct 18, 2022 | Oct 21, 2022 | bar: Date Oct 18 to Date Oct 21
2.4. Delete submitted paper (Author)
2.4.1. Planning
2.4.1.1. User Story | Less than a day | Oct 14, 2022 | Oct 14, 2022 | bar: Date Oct 14
2.4.1.2. Use Case Description | 2 days | Oct 14, 2022 | Oct 15, 2022 | bar: Date Oct 14 to Date Oct 15
2.4.2. Designs
2.4.2.1. BCE + UML Diagram | 2 days | Oct 15, 2022 | Oct 16, 2022 | bar: Date Oct 15 to Date Oct 16
2.4.2.2. Sequence Diagram | 2 days | Oct 16, 2022 | Oct 17, 2022 | bar: Date Oct 16 to Date Oct 17
2.4.2.3. Wireframe | Less than a day | Oct 17, 2022 | Oct 17, 2022 | bar: Date Oct 17
2.4.2.4. Data Persistent | 2 days | Oct 16, 2022 | Oct 17, 2022 | bar: Date Oct 16 to Date Oct 17
2.4.2.5. Test Case | 2 days | Oct 16, 2022 | Oct 17, 2022 | bar: Date Oct 16 to Date Oct 17
2.4.3. Programming
2.4.3.1. Front-end Programming | 2 days | Oct 17, 2022 | Oct 18, 2022 | bar: Date Oct 17 to Date Oct 18
2.4.3.2. Back-end Programming | 2 days | Oct 17, 2022 | Oct 18, 2022 | bar: Date Oct 17 to Date Oct 18
2.4.3. Testing | 4 days | Oct 18, 2022 | Oct 21, 2022 | bar: Date Oct 18 to Date Oct 21
2.5. Read submitted paper (Author)
2.5.1. Planning
2.5.1.1. User Story | Less than a day | Oct 14, 2022 | Oct 14, 2022 | bar: Date Oct 14
2.5.1.2. Use Case Description | 2 days | Oct 14, 2022 | Oct 15, 2022 | bar: Date Oct 14 to Date Oct 15
2.5.2. Designs
2.5.2.1. BCE + UML Diagram | 2 days | Oct 15, 2022 | Oct 16, 2022 | bar: Date Oct 15 to Date Oct 16
2.5.2.2. Sequence Diagram | 2 days | Oct 16, 2022 | Oct 17, 2022 | bar: Date Oct 16 to Date Oct 17
2.5.2.3. Wireframe | Less than a day | Oct 17, 2022 | Oct 17, 2022 | bar: Date Oct 17
2.5.2.4. Data Persistent | 2 days | Oct 16, 2022 | Oct 17, 2022 | bar: Date Oct 16 to Date Oct 17
2.5.2.5. Test Case | 2 days | Oct 16, 2022 | Oct 17, 2022 | bar: Date Oct 16 to Date Oct 17
2.5.3. Programming
2.5.3.1. Front-end Programming | 2 days | Oct 17, 2022 | Oct 18, 2022 | bar: Date Oct 17 to Date Oct 18
2.5.3.2. Back-end Programming | 2 days | Oct 17, 2022 | Oct 18, 2022 | bar: Date Oct 17 to Date Oct 18
2.5.3. Testing | 4 days | Oct 18, 2022 | Oct 21, 2022 | bar: Date Oct 18 to Date Oct 21
2.6. Class Diagram | 3 days | Oct 19, 2022 | Oct 21, 2022 | bar: Date Oct 19 to Date Oct 21