## 시트1
Task Name | Duration | Start | End | Date
|  |  |  | Oct 21 | Oct 22 | Oct 23 | Oct 24 | Oct 25 | Oct 26 | Oct 27 | Oct 28
1. External Tasks
1.1. Task distribution for each members | Less than a day | Oct 21, 2022 | Oct 21, 2022 | bar: Date Oct 21
1.2. Create a list of prioritized use cases | Less than a day | Oct 21, 2022 | Oct 21, 2022 | bar: Date Oct 21
1.3. Taiga follow-up as project management software | Less than a day | Oct 21, 2022 | Oct 21, 2022 | bar: Date Oct 21
1.4. Google Drive follow-up as the files repository | Less than a day | Oct 21, 2022 | Oct 21, 2022 | bar: Date Oct 21
2. Software Development (per user story)
2.1. Set the max number of papers (Reviewer)
2.1.1. Planning
2.1.1.1. User Story | Less than a day | Oct 21, 2022 | Oct 21, 2022 | bar: Date Oct 21
2.1.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 22, 2022 | bar: Date Oct 21 to Date Oct 22
2.1.2. Designs
2.1.2.1. BCE + UML Diagram | 2 days | Oct 22, 2022 | Oct 23, 2022 | bar: Date Oct 22 to Date Oct 23
2.1.2.2. Sequence Diagram | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.1.2.3. Wireframe | Less than a day | Oct 24, 2022 | Oct 24, 2022 | bar: Date Oct 24
2.1.2.4. Data Persistent | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.1.2.5. Test Case | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.1.3. Programming
2.1.3.1. Front-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.1.3.2. Back-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.1.3. Testing | 4 days | Oct 25, 2022 | Oct 28, 2022 | bar: Date Oct 25 to Date Oct 28
2.2. Bid for a paper (Reviewer)
2.2.1. Planning
2.2.1.1. User Story | Less than a day | Oct 21, 2022 | Oct 21, 2022 | bar: Date Oct 21
2.2.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 22, 2022 | bar: Date Oct 21 to Date Oct 22
2.2.2. Designs
2.2.2.1. BCE + UML Diagram | 2 days | Oct 22, 2022 | Oct 23, 2022 | bar: Date Oct 22 to Date Oct 23
2.2.2.2. Sequence Diagram | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.2.2.3. Wireframe | Less than a day | Oct 24, 2022 | Oct 24, 2022 | bar: Date Oct 24
2.2.2.4. Data Persistent | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.2.2.5. Test Case | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.2.3. Programming
2.2.3.1. Front-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.2.3.2. Back-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.2.3. Testing | 4 days | Oct 25, 2022 | Oct 28, 2022 | bar: Date Oct 25 to Date Oct 28
2.3. View bidded paper (Reviewer)
2.3.1. Planning
2.3.1.1. User Story | Less than a day | Oct 21, 2022 | Oct 21, 2022 | bar: Date Oct 21
2.3.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 22, 2022 | bar: Date Oct 21 to Date Oct 22
2.3.2. Designs
2.3.2.1. BCE + UML Diagram | 2 days | Oct 22, 2022 | Oct 23, 2022 | bar: Date Oct 22 to Date Oct 23
2.3.2.2. Sequence Diagram | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.3.2.3. Wireframe | Less than a day | Oct 24, 2022 | Oct 24, 2022 | bar: Date Oct 24
2.3.2.4. Data Persistent | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.3.2.5. Test Case | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.3.3. Programming
2.3.3.1. Front-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.3.3.2. Back-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.3.3. Testing | 4 days | Oct 25, 2022 | Oct 28, 2022 | bar: Date Oct 25 to Date Oct 28
2.4. Delete bidded paper (Reviewer)
2.4.1. Planning
2.4.1.1. User Story | Less than a day | Oct 21, 2022 | Oct 21, 2022 | bar: Date Oct 21
2.4.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 22, 2022 | bar: Date Oct 21 to Date Oct 22
2.4.2. Designs
2.4.2.1. BCE + UML Diagram | 2 days | Oct 22, 2022 | Oct 23, 2022 | bar: Date Oct 22 to Date Oct 23
2.4.2.2. Sequence Diagram | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.4.2.3. Wireframe | Less than a day | Oct 24, 2022 | Oct 24, 2022 | bar: Date Oct 24
2.4.2.4. Data Persistent | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.4.2.5. Test Case | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.4.3. Programming
2.4.3.1. Front-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.4.3.2. Back-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.4.3. Testing | 4 days | Oct 25, 2022 | Oct 28, 2022 | bar: Date Oct 25 to Date Oct 28
2.5. View assigned paper (Reviewer)
2.5.1. Planning
2.5.1.1. User Story | Less than a day | Oct 21, 2022 | Oct 21, 2022 | bar: Date Oct 21
2.5.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 22, 2022 | bar: Date Oct 21 to Date Oct 22
2.5.2. Designs
2.5.2.1. BCE + UML Diagram | 2 days | Oct 22, 2022 | Oct 23, 2022 | bar: Date Oct 22 to Date Oct 23
2.5.2.2. Sequence Diagram | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.5.2.3. Wireframe | Less than a day | Oct 24, 2022 | Oct 24, 2022 | bar: Date Oct 24
2.5.2.4. Data Persistent | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.5.2.5. Test Case | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.5.3. Programming
2.5.3.1. Front-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.5.3.2. Back-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.5.3. Testing | 4 days | Oct 25, 2022 | Oct 28, 2022 | bar: Date Oct 25 to Date Oct 28
2.6. Submit review (Reviewer)
2.6.1. Planning
2.6.1.1. User Story | Less than a day | Oct 21, 2022 | Oct 21, 2022 | bar: Date Oct 21
2.6.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 22, 2022 | bar: Date Oct 21 to Date Oct 22
2.6.2. Designs
2.6.2.1. BCE + UML Diagram | 2 days | Oct 22, 2022 | Oct 23, 2022 | bar: Date Oct 22 to Date Oct 23
2.6.2.2. Sequence Diagram | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.6.2.3. Wireframe | Less than a day | Oct 24, 2022 | Oct 24, 2022 | bar: Date Oct 24
2.6.2.4. Data Persistent | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.6.2.5. Test Case | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.6.3. Programming
2.6.3.1. Front-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.6.3.2. Back-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.6.3. Testing | 4 days | Oct 25, 2022 | Oct 28, 2022 | bar: Date Oct 25 to Date Oct 28
2.7. View bidded paper of all reviewer(Conference Chair)
2.7.1. Planning
2.7.1.1. User Story | Less than a day | Oct 21, 2022 | Oct 21, 2022 | bar: Date Oct 21
2.7.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 22, 2022 | bar: Date Oct 21 to Date Oct 22
2.7.2. Designs
2.7.2.1. BCE + UML Diagram | 2 days | Oct 22, 2022 | Oct 23, 2022 | bar: Date Oct 22 to Date Oct 23
2.7.2.2. Sequence Diagram | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.7.2.3. Wireframe | Less than a day | Oct 24, 2022 | Oct 24, 2022 | bar: Date Oct 24
2.7.2.4. Data Persistent | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.7.2.5. Test Case | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.7.3. Programming
2.7.3.1. Front-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.7.3.2. Back-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.7.3. Testing | 4 days | Oct 25, 2022 | Oct 28, 2022 | bar: Date Oct 25 to Date Oct 28
2.8. Allocate papers to reviewers manually (Conference Chair)
2.8.1. Planning
2.8.1.1. User Story | Less than a day | Oct 21, 2022 | Oct 21, 2022 | bar: Date Oct 21
2.8.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 22, 2022 | bar: Date Oct 21 to Date Oct 22
2.8.2. Designs
2.8.2.1. BCE + UML Diagram | 2 days | Oct 22, 2022 | Oct 23, 2022 | bar: Date Oct 22 to Date Oct 23
2.8.2.2. Sequence Diagram | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.8.2.3. Wireframe | Less than a day | Oct 24, 2022 | Oct 24, 2022 | bar: Date Oct 24
2.8.2.4. Data Persistent | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.8.2.5. Test Case | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.8.3. Programming
2.8.3.1. Front-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.8.3.2. Back-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.8.3. Testing | 4 days | Oct 25, 2022 | Oct 28, 2022 | bar: Date Oct 25 to Date Oct 28
2.9. Read paper's content (Reviewer)
2.9.1. Planning
2.9.1.1. User Story | Less than a day | Oct 21, 2022 | Oct 21, 2022 | bar: Date Oct 21
2.9.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 22, 2022 | bar: Date Oct 21 to Date Oct 22
2.9.2. Designs
2.9.2.1. BCE + UML Diagram | 2 days | Oct 22, 2022 | Oct 23, 2022 | bar: Date Oct 22 to Date Oct 23
2.9.2.2. Sequence Diagram | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.9.2.3. Wireframe | Less than a day | Oct 24, 2022 | Oct 24, 2022 | bar: Date Oct 24
2.9.2.4. Data Persistent | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.9.2.5. Test Case | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.9.3. Programming
2.9.3.1. Front-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.9.3.2. Back-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.9.3. Testing | 4 days | Oct 25, 2022 | Oct 28, 2022 | bar: Date Oct 25 to Date Oct 28
2.10. Read my review's content (Reviewer)
2.10.1. Planning
2.10.1.1. User Story | Less than a day | Oct 21, 2022 | Oct 21, 2022 | bar: Date Oct 21
2.10.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 22, 2022 | bar: Date Oct 21 to Date Oct 22
2.10.2. Designs
2.10.2.1. BCE + UML Diagram | 2 days | Oct 22, 2022 | Oct 23, 2022 | bar: Date Oct 22 to Date Oct 23
2.10.2.2. Sequence Diagram | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.10.2.3. Wireframe | Less than a day | Oct 24, 2022 | Oct 24, 2022 | bar: Date Oct 24
2.10.2.4. Data Persistent | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.10.2.5. Test Case | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.10.3. Programming
2.10.3.1. Front-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.10.3.2. Back-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.10.3. Testing | 4 days | Oct 25, 2022 | Oct 28, 2022 | bar: Date Oct 25 to Date Oct 28
2.11. View unbidded paper (Reviewer)
2.11.1. Planning
2.11.1.1. User Story | Less than a day | Oct 21, 2022 | Oct 21, 2022 | bar: Date Oct 21
2.11.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 22, 2022 | bar: Date Oct 21 to Date Oct 22
2.11.2. Designs
2.11.2.1. BCE + UML Diagram | 2 days | Oct 22, 2022 | Oct 23, 2022 | bar: Date Oct 22 to Date Oct 23
2.11.2.2. Sequence Diagram | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.11.2.3. Wireframe | Less than a day | Oct 24, 2022 | Oct 24, 2022 | bar: Date Oct 24
2.11.2.4. Data Persistent | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.11.2.5. Test Case | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.11.3. Programming
2.11.3.1. Front-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
211.3.2. Back-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.11.3. Testing | 4 days | Oct 25, 2022 | Oct 28, 2022 | bar: Date Oct 25 to Date Oct 28
2.12. Unallocate paper assigned to reviewer(Conference Chair)
2.12.1. Planning
2.12.1.1. User Story | Less than a day | Oct 21, 2022 | Oct 21, 2022 | bar: Date Oct 21
2.12.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 22, 2022 | bar: Date Oct 21 to Date Oct 22
2.12.2. Designs
2.12.2.1. BCE + UML Diagram | 2 days | Oct 22, 2022 | Oct 23, 2022 | bar: Date Oct 22 to Date Oct 23
2.12.2.2. Sequence Diagram | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.12.2.3. Wireframe | Less than a day | Oct 24, 2022 | Oct 24, 2022 | bar: Date Oct 24
2.12.2.4. Data Persistent | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.12.2.5. Test Case | 2 days | Oct 23, 2022 | Oct 24, 2022 | bar: Date Oct 23 to Date Oct 24
2.12.3. Programming
2.12.3.1. Front-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.12.3.2. Back-end Programming | 2 days | Oct 24, 2022 | Oct 25, 2022 | bar: Date Oct 24 to Date Oct 25
2.12.3. Testing | 4 days | Oct 25, 2022 | Oct 28, 2022 | bar: Date Oct 25 to Date Oct 28
2.13. Class Diagram | 3 days | Oct 26, 2022 | Oct 28, 2022 | bar: Date Oct 26 to Date Oct 28