## 시트1
Task Name | Duration | Start | End | Date
|  |  |  | Oct 28 | Oct 29 | Oct 30 | Oct 31 | Nov 1 | Nov 2 | Nov 3 | Nov 4
1. External Tasks
1.1. Task distribution for each members | Less than a day | Oct 28, 2022 | Oct 28, 2022 | bar: Date Oct 28
1.2. Create a list of prioritized use cases | Less than a day | Oct 28, 2022 | Oct 28, 2022 | bar: Date Oct 28
1.3. Taiga follow-up as project management software | Less than a day | Oct 28, 2022 | Oct 28, 2022 | bar: Date Oct 28
1.4. Google Drive follow-up as the files repository | Less than a day | Oct 28, 2022 | Oct 28, 2022 | bar: Date Oct 28
2. Software Development (per user story)
2.1. Read other reviewer's review of the paper (Reviewer)
2.1.1. Planning
2.1.1.1. User Story | Less than a day | Oct 28, 2022 | Oct 28, 2022 | bar: Date Oct 28
2.1.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 29, 2022 | bar: Date Oct 28 to Date Oct 29
2.1.2. Designs
2.1.2.1. BCE + UML Diagram | 2 days | Oct 29, 2022 | Oct 30, 2022 | bar: Date Oct 29 to Date Oct 30
2.1.2.2. Sequence Diagram | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.1.2.3. Wireframe | Less than a day | Nov 1, 2022 | Nov 1, 2022 | bar: Date Oct 31
2.1.2.4. Data Persistent | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.1.2.5. Test Case | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.1.3. Programming
2.1.3.1. Front-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.1.3.2. Back-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.1.3. Testing | 4 days | Nov 1, 2022 | Nov 4, 2022 | bar: Date Nov 1 to Date Nov 4
2.2. Edit my own review (Reviewer)
2.2.1. Planning
2.2.1.1. User Story | Less than a day | Oct 28, 2022 | Oct 28, 2022 | bar: Date Oct 28
2.2.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 29, 2022 | bar: Date Oct 28 to Date Oct 29
2.2.2. Designs
2.2.2.1. BCE + UML Diagram | 2 days | Oct 29, 2022 | Oct 30, 2022 | bar: Date Oct 29 to Date Oct 30
2.2.2.2. Sequence Diagram | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.2.2.3. Wireframe | Less than a day | Nov 1, 2022 | Nov 1, 2022 | bar: Date Oct 31
2.2.2.4. Data Persistent | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.2.2.5. Test Case | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.2.3. Programming
2.2.3.1. Front-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.2.3.2. Back-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.2.3. Testing | 4 days | Nov 1, 2022 | Nov 4, 2022 | bar: Date Nov 1 to Date Nov 4
2.3. Comment on the review made by other reviewers (Reviewer)
2.3.1. Planning
2.3.1.1. User Story | Less than a day | Oct 28, 2022 | Oct 28, 2022 | bar: Date Oct 28
2.3.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 29, 2022 | bar: Date Oct 28 to Date Oct 29
2.3.2. Designs
2.3.2.1. BCE + UML Diagram | 2 days | Oct 29, 2022 | Oct 30, 2022 | bar: Date Oct 29 to Date Oct 30
2.3.2.2. Sequence Diagram | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.3.2.3. Wireframe | Less than a day | Nov 1, 2022 | Nov 1, 2022 | bar: Date Oct 31
2.3.2.4. Data Persistent | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.3.2.5. Test Case | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.3.3. Programming
2.3.3.1. Front-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.3.3.2. Back-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.3.3. Testing | 4 days | Nov 1, 2022 | Nov 4, 2022 | bar: Date Nov 1 to Date Nov 4
2.4. Delete my own review (Reviewer)
2.4.1. Planning
2.4.1.1. User Story | Less than a day | Oct 28, 2022 | Oct 28, 2022 | bar: Date Oct 28
2.4.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 29, 2022 | bar: Date Oct 28 to Date Oct 29
2.4.2. Designs
2.4.2.1. BCE + UML Diagram | 2 days | Oct 29, 2022 | Oct 30, 2022 | bar: Date Oct 29 to Date Oct 30
2.4.2.2. Sequence Diagram | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.4.2.3. Wireframe | Less than a day | Nov 1, 2022 | Nov 1, 2022 | bar: Date Oct 31
2.4.2.4. Data Persistent | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.4.2.5. Test Case | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.4.3. Programming
2.4.3.1. Front-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.4.3.2. Back-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.4.3. Testing | 4 days | Nov 1, 2022 | Nov 4, 2022 | bar: Date Nov 1 to Date Nov 4
2.5. View all undecided papers (Conference Chair)
2.5.1. Planning
2.5.1.1. User Story | Less than a day | Oct 28, 2022 | Oct 28, 2022 | bar: Date Oct 28
2.5.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 29, 2022 | bar: Date Oct 28 to Date Oct 29
2.5.2. Designs
2.5.2.1. BCE + UML Diagram | 2 days | Oct 29, 2022 | Oct 30, 2022 | bar: Date Oct 29 to Date Oct 30
2.5.2.2. Sequence Diagram | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.5.2.3. Wireframe | Less than a day | Nov 1, 2022 | Nov 1, 2022 | bar: Date Oct 31
2.5.2.4. Data Persistent | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.5.2.5. Test Case | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.5.3. Programming
2.5.3.1. Front-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.5.3.2. Back-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.5.3. Testing | 4 days | Nov 1, 2022 | Nov 4, 2022 | bar: Date Nov 1 to Date Nov 4
2.6. Accept paper (Conference Chair)
2.6.1. Planning
2.6.1.1. User Story | Less than a day | Oct 28, 2022 | Oct 28, 2022 | bar: Date Oct 28
2.6.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 29, 2022 | bar: Date Oct 28 to Date Oct 29
2.6.2. Designs
2.6.2.1. BCE + UML Diagram | 2 days | Oct 29, 2022 | Oct 30, 2022 | bar: Date Oct 29 to Date Oct 30
2.6.2.2. Sequence Diagram | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.6.2.3. Wireframe | Less than a day | Nov 1, 2022 | Nov 1, 2022 | bar: Date Oct 31
2.6.2.4. Data Persistent | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.6.2.5. Test Case | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.6.3. Programming
2.6.3.1. Front-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.6.3.2. Back-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.6.3. Testing | 4 days | Nov 1, 2022 | Nov 4, 2022 | bar: Date Nov 1 to Date Nov 4
2.7. Reject paper (Conference Chair)
2.7.1. Planning
2.7.1.1. User Story | Less than a day | Oct 28, 2022 | Oct 28, 2022 | bar: Date Oct 28
2.7.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 29, 2022 | bar: Date Oct 28 to Date Oct 29
2.7.2. Designs
2.7.2.1. BCE + UML Diagram | 2 days | Oct 29, 2022 | Oct 30, 2022 | bar: Date Oct 29 to Date Oct 30
2.7.2.2. Sequence Diagram | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.7.2.3. Wireframe | Less than a day | Nov 1, 2022 | Nov 1, 2022 | bar: Date Oct 31
2.7.2.4. Data Persistent | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.7.2.5. Test Case | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.7.3. Programming
2.7.3.1. Front-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.7.3.2. Back-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.7.3. Testing | 4 days | Nov 1, 2022 | Nov 4, 2022 | bar: Date Nov 1 to Date Nov 4
2.8. View list of accepted and rejected papers (Conference Chair)
2.8.1. Planning
2.8.1.1. User Story | Less than a day | Oct 28, 2022 | Oct 28, 2022 | bar: Date Oct 28
2.8.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 29, 2022 | bar: Date Oct 28 to Date Oct 29
2.8.2. Designs
2.8.2.1. BCE + UML Diagram | 2 days | Oct 29, 2022 | Oct 30, 2022 | bar: Date Oct 29 to Date Oct 30
2.8.2.2. Sequence Diagram | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.8.2.3. Wireframe | Less than a day | Nov 1, 2022 | Nov 1, 2022 | bar: Date Oct 31
2.8.2.4. Data Persistent | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.8.2.5. Test Case | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.8.3. Programming
2.8.3.1. Front-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.8.3.2. Back-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.8.3. Testing | 4 days | Nov 1, 2022 | Nov 4, 2022 | bar: Date Nov 1 to Date Nov 4
2.9. Read review's content (Conference Chair)
2.9.1. Planning
2.9.1.1. User Story | Less than a day | Oct 28, 2022 | Oct 28, 2022 | bar: Date Oct 28
2.9.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 29, 2022 | bar: Date Oct 28 to Date Oct 29
2.9.2. Designs
2.9.2.1. BCE + UML Diagram | 2 days | Oct 29, 2022 | Oct 30, 2022 | bar: Date Oct 29 to Date Oct 30
2.9.2.2. Sequence Diagram | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.9.2.3. Wireframe | Less than a day | Nov 1, 2022 | Nov 1, 2022 | bar: Date Oct 31
2.9.2.4. Data Persistent | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.9.2.5. Test Case | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.9.3. Programming
2.9.3.1. Front-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.9.3.2. Back-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.9.3. Testing | 4 days | Nov 1, 2022 | Nov 4, 2022 | bar: Date Nov 1 to Date Nov 4
2.10. Read paper's content (Conference Chair)
2.10.1. Planning
2.10.1.1. User Story | Less than a day | Oct 28, 2022 | Oct 28, 2022 | bar: Date Oct 28
2.10.1.2 Use Case Description | 2 days | Oct 21, 2022 | Oct 29, 2022 | bar: Date Oct 28 to Date Oct 29
2.10.2. Designs
2.10.2.1. BCE + UML Diagram | 2 days | Oct 29, 2022 | Oct 30, 2022 | bar: Date Oct 29 to Date Oct 30
2.10.2.2. Sequence Diagram | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.10.2.3. Wireframe | Less than a day | Nov 1, 2022 | Nov 1, 2022 | bar: Date Oct 31
2.10.2.4. Data Persistent | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.10.2.5. Test Case | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.10.3. Programming
2.10.3.1. Front-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.10.3.2. Back-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.10.3. Testing | 4 days | Nov 1, 2022 | Nov 4, 2022 | bar: Date Nov 1 to Date Nov 4
2.11. View comments on the review (Reviewer)
2.11.1. Planning
2.11.1.1. User Story | Less than a day | Oct 28, 2022 | Oct 28, 2022 | bar: Date Oct 28
2.11.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 29, 2022 | bar: Date Oct 28 to Date Oct 29
2.11.2. Designs
2.11.2.1. BCE + UML Diagram | 2 days | Oct 29, 2022 | Oct 30, 2022 | bar: Date Oct 29 to Date Oct 30
2.11.2.2. Sequence Diagram | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.11.2.3. Wireframe | Less than a day | Nov 1, 2022 | Nov 1, 2022 | bar: Date Oct 31
2.11.2.4. Data Persistent | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.11.2.5. Test Case | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.11.3. Programming
2.11.3.1. Front-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.11.3.2. Back-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.11.3. Testing | 4 days | Nov 1, 2022 | Nov 4, 2022 | bar: Date Nov 1 to Date Nov 4
2.12. View reviewed papers (Reviewer)
2.12.1. Planning
2.12.1.1. User Story | Less than a day | Oct 28, 2022 | Oct 28, 2022 | bar: Date Oct 28
2.12.1.2. Use Case Description | 2 days | Oct 21, 2022 | Oct 29, 2022 | bar: Date Oct 28 to Date Oct 29
2.12.2. Designs
2.12.2.1. BCE + UML Diagram | 2 days | Oct 29, 2022 | Oct 30, 2022 | bar: Date Oct 29 to Date Oct 30
2.12.2.2. Sequence Diagram | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.12.2.3. Wireframe | Less than a day | Nov 1, 2022 | Nov 1, 2022 | bar: Date Oct 31
2.12.2.4. Data Persistent | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.12.2.5. Test Case | 2 days | Oct 30, 2022 | Nov 1, 2022 | bar: Date Oct 30 to Date Oct 31
2.12.3. Programming
2.12.3.1. Front-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.12.3.2. Back-end Programming | 2 days | Oct 31, 2022 | Nov 1, 2022 | bar: Date Oct 31 to Date Nov 1
2.12.3. Testing | 4 days | Nov 1, 2022 | Nov 4, 2022 | bar: Date Nov 1 to Date Nov 4
2.13. Class Diagram | 3 days | Nov 2, 2022 | Nov 4, 2022 | bar: Date Nov 2 to Date Nov 4