## 시트1
Task Name | Duration | Start | End | Date
|  |  |  | Nov 4 | Nov 5 | Nov 6 | Nov 7 | Nov 8 | Nov 9 | Nov 10 | Nov 11
1. External Tasks
1.1. Task distribution for each members | Less than a day | Nov 4, 2022 | Nov 4, 2022 | bar: Date Nov 4
1.2. Create a list of prioritized use cases | Less than a day | Nov 4, 2022 | Nov 4, 2022 | bar: Date Nov 4
1.3. Taiga follow-up as project management software | Less than a day | Nov 4, 2022 | Nov 4, 2022 | bar: Date Nov 4
1.4. Google Drive follow-up as the files repository | Less than a day | Nov 4, 2022 | Nov 4, 2022 | bar: Date Nov 4
2. Software Development (per user story)
2.1. Rate the reviews of my own papers (Author)
2.1.1. Planning
2.1.1.1. User Story | Less than a day | Nov 4, 2022 | Nov 4, 2022 | bar: Date Nov 4
2.1.1.2. Use Case Description | 2 days | Nov 4, 2022 | Nov 5, 2022 | bar: Date Nov 4 to Date Nov 5
2.1.2. Designs
2.1.2.1. BCE + UML Diagram | 2 days | Nov 5, 2022 | Nov 6, 2022 | bar: Date Nov 5 to Date Nov 6
2.1.2.2. Sequence Diagram | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.1.2.3. Wireframe | Less than a day | Nov 7, 2022 | Nov 7, 2022 | bar: Date Nov 7
2.1.2.4. Data Persistent | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.1.2.5. Test Case | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.1.3. Programming
2.1.3.1. Front-end Programming | 2 days | Nov 7, 2022 | Nov 8, 2022 | bar: Date Nov 7 to Date Nov 8
2.1.3.2. Back-end Programming | 2 days | Nov 7, 2022 | Nov 8, 2022 | bar: Date Nov 7 to Date Nov 8
2.1.3. Testing | 4 days | Nov 8, 2022 | Nov 11, 2022 | bar: Date Nov 8 to Date Nov 11
2.2. View reviews of my own & co-author papers (Author)
2.2.1. Planning
2.2.1.1. User Story | Less than a day | Nov 4, 2022 | Nov 4, 2022 | bar: Date Nov 4
2.2.1.2. Use Case Description | 2 days | Nov 4, 2022 | Nov 5, 2022 | bar: Date Nov 4 to Date Nov 5
2.2.2. Designs
2.2.2.1. BCE + UML Diagram | 2 days | Nov 5, 2022 | Nov 6, 2022 | bar: Date Nov 5 to Date Nov 6
2.2.2.2. Sequence Diagram | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.2.2.3. Wireframe | Less than a day | Nov 7, 2022 | Nov 7, 2022 | bar: Date Nov 7
2.2.2.4. Data Persistent | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.2.2.5. Test Case | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.2.3. Programming
2.2.3.1. Front-end Programming | 2 days | Nov 7, 2022 | Nov 8, 2022 | bar: Date Nov 7 to Date Nov 8
2.2.3.2. Back-end Programming | 2 days | Nov 7, 2022 | Nov 8, 2022 | bar: Date Nov 7 to Date Nov 8
2.2.3. Testing | 4 days | Nov 8, 2022 | Nov 11, 2022 | bar: Date Nov 8 to Date Nov 11
2.3. Cancel paper decision (Conference Chair)
2.3.1. Planning
2.3.1.1. User Story | Less than a day | Nov 4, 2022 | Nov 4, 2022 | bar: Date Nov 4
2.3.1.2. Use Case Description | 2 days | Nov 4, 2022 | Nov 5, 2022 | bar: Date Nov 4 to Date Nov 5
2.3.2. Designs
2.3.2.1. BCE + UML Diagram | 2 days | Nov 5, 2022 | Nov 6, 2022 | bar: Date Nov 5 to Date Nov 6
2.3.2.2. Sequence Diagram | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.3.2.3. Wireframe | Less than a day | Nov 7, 2022 | Nov 7, 2022 | bar: Date Nov 7
2.3.2.4. Data Persistent | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.3.2.5. Test Case | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.3.3. Programming
2.3.3.1. Front-end Programming | 2 days | Nov 7, 2022 | Nov 8, 2022 | bar: Date Nov 7 to Date Nov 8
2.3.3.2. Back-end Programming | 2 days | Nov 7, 2022 | Nov 8, 2022 | bar: Date Nov 7 to Date Nov 8
2.3.3. Testing | 4 days | Nov 8, 2022 | Nov 11, 2022 | bar: Date Nov 8 to Date Nov 11
2.4. Delete the review rating of my own papers (Author)
2.4.1. Planning
2.4.1.1. User Story | Less than a day | Nov 4, 2022 | Nov 4, 2022 | bar: Date Nov 4
2.4.1.2. Use Case Description | 2 days | Nov 4, 2022 | Nov 5, 2022 | bar: Date Nov 4 to Date Nov 5
2.4.2. Designs
2.4.2.1. BCE + UML Diagram | 2 days | Nov 5, 2022 | Nov 6, 2022 | bar: Date Nov 5 to Date Nov 6
2.4.2.2. Sequence Diagram | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.4.2.3. Wireframe | Less than a day | Nov 7, 2022 | Nov 7, 2022 | bar: Date Nov 7
2.4.2.4. Data Persistent | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.4.2.5. Test Case | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.4.3. Programming
2.4.3.1. Front-end Programming | 2 days | Nov 7, 2022 | Nov 8, 2022 | bar: Date Nov 7 to Date Nov 8
2.4.3.2. Back-end Programming | 2 days | Nov 7, 2022 | Nov 8, 2022 | bar: Date Nov 7 to Date Nov 8
2.4.3. Testing | 4 days | Nov 8, 2022 | Nov 11, 2022 | bar: Date Nov 8 to Date Nov 11
2.5. Edit submitted comment (Reviewer)
2.5.1. Planning
2.5.1.1. User Story | Less than a day | Nov 4, 2022 | Nov 4, 2022 | bar: Date Nov 4
2.5.1.2. Use Case Description | 2 days | Nov 4, 2022 | Nov 5, 2022 | bar: Date Nov 4 to Date Nov 5
2.5.2. Designs
2.5.2.1. BCE + UML Diagram | 2 days | Nov 5, 2022 | Nov 6, 2022 | bar: Date Nov 5 to Date Nov 6
2.5.2.2. Sequence Diagram | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.5.2.3. Wireframe | Less than a day | Nov 7, 2022 | Nov 7, 2022 | bar: Date Nov 7
2.5.2.4. Data Persistent | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.5.2.5. Test Case | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.5.3. Programming
2.5.3.1. Front-end Programming | 2 days | Nov 7, 2022 | Nov 8, 2022 | bar: Date Nov 7 to Date Nov 8
2.5.3.2. Back-end Programming | 2 days | Nov 7, 2022 | Nov 8, 2022 | bar: Date Nov 7 to Date Nov 8
2.5.3. Testing | 4 days | Nov 8, 2022 | Nov 11, 2022 | bar: Date Nov 8 to Date Nov 11
2.6. Delete submitted comment (Reviewer)
2.6.1. Planning
2.6.1.1. User Story | Less than a day | Nov 4, 2022 | Nov 4, 2022 | bar: Date Nov 4
2.6.1.2. Use Case Description | 2 days | Nov 4, 2022 | Nov 5, 2022 | bar: Date Nov 4 to Date Nov 5
2.6.2. Designs
2.6.2.1. BCE + UML Diagram | 2 days | Nov 5, 2022 | Nov 6, 2022 | bar: Date Nov 5 to Date Nov 6
2.6.2.2. Sequence Diagram | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.6.2.3. Wireframe | Less than a day | Nov 7, 2022 | Nov 7, 2022 | bar: Date Nov 7
2.6.2.4. Data Persistent | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.6.2.5. Test Case | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.6.3. Programming
2.6.3.1. Front-end Programming | 2 days | Nov 7, 2022 | Nov 8, 2022 | bar: Date Nov 7 to Date Nov 8
2.6.3.2. Back-end Programming | 2 days | Nov 7, 2022 | Nov 8, 2022 | bar: Date Nov 7 to Date Nov 8
2.6.3. Testing | 4 days | Nov 8, 2022 | Nov 11, 2022 | bar: Date Nov 8 to Date Nov 11
2.7. View rated reviews (Author)
2.7.1. Planning
2.7.1.1. User Story | Less than a day | Nov 4, 2022 | Nov 4, 2022 | bar: Date Nov 4
2.7.1.2. Use Case Description | 2 days | Nov 4, 2022 | Nov 5, 2022 | bar: Date Nov 4 to Date Nov 5
2.7.2. Designs
2.7.2.1. BCE + UML Diagram | 2 days | Nov 5, 2022 | Nov 6, 2022 | bar: Date Nov 5 to Date Nov 6
2.7.2.2. Sequence Diagram | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.7.2.3. Wireframe | Less than a day | Nov 7, 2022 | Nov 7, 2022 | bar: Date Nov 7
2.7.2.4. Data Persistent | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.7.2.5. Test Case | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.7.3. Programming
2.7.3.1. Front-end Programming | 2 days | Nov 7, 2022 | Nov 8, 2022 | bar: Date Nov 7 to Date Nov 8
2.7.3.2. Back-end Programming | 2 days | Nov 7, 2022 | Nov 8, 2022 | bar: Date Nov 7 to Date Nov 8
2.7.3. Testing | 4 days | Nov 8, 2022 | Nov 11, 2022 | bar: Date Nov 8 to Date Nov 11
2.8. Review review's content (Author)
2.8.1. Planning
2.8.1.1. User Story | Less than a day | Nov 4, 2022 | Nov 4, 2022 | bar: Date Nov 4
2.8.1.2. Use Case Description | 2 days | Nov 4, 2022 | Nov 5, 2022 | bar: Date Nov 4 to Date Nov 5
2.8.2. Designs
2.8.2.1. BCE + UML Diagram | 2 days | Nov 5, 2022 | Nov 6, 2022 | bar: Date Nov 5 to Date Nov 6
2.8.2.2. Sequence Diagram | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.8.2.3. Wireframe | Less than a day | Nov 7, 2022 | Nov 7, 2022 | bar: Date Nov 7
2.8.2.4. Data Persistent | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.8.2.5. Test Case | 2 days | Nov 6, 2022 | Nov 7, 2022 | bar: Date Nov 6 to Date Nov 7
2.8.3. Programming
2.8.3.1. Front-end Programming | 2 days | Nov 7, 2022 | Nov 8, 2022 | bar: Date Nov 7 to Date Nov 8
2.8.3.2. Back-end Programming | 2 days | Nov 7, 2022 | Nov 8, 2022 | bar: Date Nov 7 to Date Nov 8
2.8.3. Testing | 4 days | Nov 8, 2022 | Nov 11, 2022 | bar: Date Nov 8 to Date Nov 11
2.9. Class Diagram | 3 days | Nov 9, 2022 | Nov 11, 2022 | bar: Date Nov 9 to Date Nov 11