## 시트1
Task Name | Duration | Start | End | Date
|  |  |  | Nov 11 | Nov 12 | Nov 13 | Nov 14 | Nov 15 | Nov 16 | Nov 17
1. External Tasks
1.1. Add user stories from backlogs | Less than a day | Nov 11, 2022 | Nov 11, 2022
1.2. Create a list of prioritized use cases | Less than a day | Nov 11, 2022 | Nov 11, 2022
1.3. Taiga follow-up as project management software | Less than a day | Nov 11, 2022 | Nov 11, 2022
1.4. Google Drive follow-up as the files repository | Less than a day | Nov 11, 2022 | Nov 11, 2022
1.5. Final report | 7 days | Nov 11, 2022 | Nov 17, 2022
1.6. Task distributions for each of the members | Less than a day | Nov 11, 2022 | Nov 11, 2022
2. Software Development (per user story)
2.1. Allocate papers to reviewers automatically (Conference Chair)
2.1.1. Planning
2.1.1.1. User Story | Less than a day | Nov 11, 2022 | Nov 11, 2022
2.1.1.2. Use Case Description | 2 days | Nov 11, 2022 | Nov 12, 2022
2.1.2. Designs
2.1.2.1. BCE + UML Diagram | 2 days | Nov 12, 2022 | Nov 13, 2022
2.1.2.2. Sequence Diagram | 2 days | Nov 13, 2022 | Nov 14, 2022
2.1.2.3. Wireframe | Less than a day | Nov 14, 2022 | Nov 14, 2022
2.1.2.4. Data Persistent | 2 days | Nov 13, 2022 | Nov 14, 2022
2.1.2.5. Test Case | 2 days | Nov 13, 2022 | Nov 14, 2022
2.1.3. Programming
2.1.3.1. Front-end Programming | 2 days | Nov 14, 2022 | Nov 15, 2022
2.1.3.2. Back-end Programming | 2 days | Nov 14, 2022 | Nov 15, 2022
2.1.3. Testing | 4 days | Nov 15, 2022 | Nov 17, 2022
2.2. Class Diagram | 2 days | Nov 15, 2022 | Nov 16, 2022